## Datapoints Hackaton
Customer info |  | Fiber Ordering & Delivery | [8 empty] | NaaS Pre-Design |  |  | Site Survey & Documentation |  |  | Supplier Hardware Lead Time (days)
Customer Site Contact | Pricing Model | Facility ID | Address | Location (Kommun) | Assigned Subcontractor | Frost Period Constraint | Fiber Delivery Estimation Date | Fiber Confirmed Delivery Date | Municipality Permit Lead Time (Days) | Order Priority (1-5) | Site Category | Location Type | Customer Requirements | Requires Special Hardware | Requires Lift | Installation Type | 30
Lars Holm | Fixed Price | SITE-SE-01 | Malmvägen 14, Kiruna | Kiruna | NordGräv Teknik | Oct 15 - May 20 | 2026-11-20 | 2027-01-21 | 20 | 2 | VIP | Hospital | Minimal Disruption | Yes | No | Underground (Trenching) | 30
Anna Berg | Time & Materials | SITE-SE-02 | Storgatan 1, Malmö | Malmö | Connecta Sverige | None | 2026-10-06 | 2026-10-22 | 15 | 4 | Medium | Warehouse | Standard | No | Yes | Aerial/Facade | 30
Fredrik Lind | Fixed Price | SITE-SE-03 | Drottninggatan 55, Stockholm | Stockholm | Svea Fiber AB | Nov 20 - Apr 5 | 2026-11-15 | 2026-11-28 | 35 | 1 | Large | Office Building | After-Hours Work | Yes | No | Underground (Existing Duct) | 60
Sofia Nyström | Fixed Price | SITE-SE-04 | Avenyn 10, Göteborg | Göteborg | Connecta Sverige | Dec 10 - Mar 15 | 2026-10-31 | 2026-12-03 | 30 | 2 | Large | Retail Center | After-Hours Work | No | No | Underground (Trenching) | 60
Elin Viklund | Fixed Price | SITE-SE-05 | Björkallén 21, Umeå | Umeå | NordGräv Teknik | Nov 1 - May 1 | 2026-11-25 | 2027-01-14 | 25 | 1 | VIP | University Campus | Minimal Disruption | Yes | No | Underground (Trenching) | 60
Martin Eklund | Fixed Price | SITE-SE-06 | Hamngatan 5, Luleå | Luleå | NordGräv Teknik | Oct 20 - May 15 | 2026-12-05 | 2026-12-15 | 20 | 3 | Large | Datacenter | High Security | Yes | No | Underground (Existing Duct) | 30
Oskar Persson | Time & Materials | SITE-SE-07 | Kungsgatan 30, Uppsala | Uppsala | Svea Fiber AB | Nov 15 - Apr 10 | 2026-10-26 | 2026-11-08 | 25 | 2 | Medium | Research Park | Standard | Yes | No | Aerial/Facade | 30
Hanna Jansson | Time & Materials | SITE-SE-08 | Östra Storgatan 18, Jönköping | Jönköping | Connecta Sverige | Dec 1 - Mar 20 | 2026-10-01 | 2026-10-04 | 15 | 4 | Small | Retail Store | Standard | No | Yes | Aerial/Facade | 30
David Karlsson | Time & Materials | SITE-SE-09 | Stortorget 9, Lund | Lund | Connecta Sverige | Dec 20 - Mar 1 | 2026-10-21 | 2026-11-11 | 20 | 5 | Medium | Residential Complex | Standard | No | No | Underground (Trenching) | 45
Maria Forsberg | Fixed Price | SITE-SE-10 | Frösövägen 45, Östersund | Östersund | NordGräv Teknik | Oct 25 - May 10 | 2026-11-10 | 2026-11-22 | 25 | 3 | Medium | Government Office | High Security | Yes | No | Underground (Existing Duct) | 45
Anders Nilsson | Fixed Price | SITE-SE-11 | Adelsgatan 2, Visby | Gotland | Svea Fiber AB | Dec 5 - Mar 15 | 2026-11-25 | 2027-01-05 | 30 | 1 | VIP | Port Authority | High Security | Yes | No | Underground (Trenching) | 60
Jonas Eriksson | Fixed Price | SITE-SE-12 | Stora Torget 1, Linköping | Linköping | Svea Fiber AB | Nov 25 - Apr 1 | 2026-10-31 | 2026-11-15 | 20 | 3 | Large | Industrial Factory | Minimal Disruption | No | No | Underground (Existing Duct) | 60
Emma Gustafsson | Time & Materials | SITE-SE-13 | Drottninggatan 2, Gävle | Gävle | Svea Fiber AB | Nov 10 - Apr 20 | 2026-10-16 | 2026-10-30 | 25 | 2 | Medium | Office Building | Standard | No | Yes | Aerial/Facade | 45
Peter Svensson | Time & Materials | SITE-SE-14 | Södergatan 11, Helsingborg | Helsingborg | Connecta Sverige | Dec 15 - Mar 5 | 2026-10-01 | 2026-10-19 | 15 | 4 | Small | Retail Store | After-Hours Work | No | Yes | Aerial/Facade | 45
Sara Lundgren | Time & Materials | SITE-SE-15 | Universitetsallén 8, Sundsvall | Sundsvall | NordGräv Teknik | Nov 5 - Apr 25 | 2026-10-21 | 2026-10-26 | 25 | 3 | Medium | Call Center | Standard | No | No | Underground (Existing Duct) | 60
Magnus Olsson | Fixed Price | SITE-SE-16 | Stora Gatan 40, Västerås | Västerås | Svea Fiber AB | Nov 20 - Apr 5 | 2026-11-05 | 2026-12-09 | 20 | 4 | Large | Logistics Hub | Standard | No | No | Underground (Trenching) | 60
Linda Johansson | Time & Materials | SITE-SE-17 | Järnvägsgatan 7, Örebro | Örebro | Svea Fiber AB | Nov 25 - Apr 10 | 2026-10-06 | 2026-10-12 | 20 | 5 | Small | Warehouse | Standard | No | No | Aerial/Facade | 30
Robert Bergman | Fixed Price | SITE-SE-18 | Kaggensgatan 1, Kalmar | Kalmar | Connecta Sverige | Dec 10 - Mar 10 | 2026-10-21 | 2026-11-07 | 15 | 3 | Medium | School | Minimal Disruption | No | No | Underground (Trenching) | 30
Björn Dahl | Fixed Price | SITE-SE-19 | Forskargränd 5, Skellefteå | Skellefteå | NordGräv Teknik | Oct 20 - May 10 | 2026-12-10 | 2027-02-03 | 30 | 1 | VIP | Battery Factory | High Security | Yes | No | Underground (Trenching) | 30
Therese Sjöberg | Fixed Price | SITE-SE-20 | Sandgärdsgatan 2, Borås | Borås | Connecta Sverige | Dec 5 - Mar 20 | 2026-11-10 | 2026-11-24 | 20 | 2 | Large | E-commerce Hub | Standard | Yes | No | Underground (Existing Duct) | 60
Datapoint from Customer Agreement
Datapoint from Customer Data Collection